## Outstanding Actions
|  | PTC May 2019 - May 2020 Outstanding Actions | Year To Date Completed | 189
|  |  | Year to Date Incomplete | 13
|  |  | Year to Date Superseeded | 12
|  |  | Total Actions | 214
Date | Committee | Action | Notes | Status
18th June 2019 | Full Council | To consider an appropriate fees policy. | Policy drafted for approval at earliest opportunity.
18th June 2019 | Full Council | Proposal of a monthly newsletter via Mailchimp. | Can be done for free via The Town Council's website and social media. Proposal going to Council in 2020.
23rd July 2019 | Full Council | Install broadband at Scott Park. | Charges were to high to be considered. Investigation ongoing.
19th November 2019 | Full Council | PTC to take a more active role in the Remeberance Parade in 2020. Clerk to set up a meeting with key stakeholders. | Clerk still to arrange a meeting with Key Stakeholdets.
19th November 2019 | Full Council | To engage SGC in a walkaround in Spring 2020 to locate any new or highlight old issues. | Deputy Clerk to arrange for after COVID-19 outbreak.
18th February 2020 | Full Council | Clerk to invite Tina Brice to a future meeting for councillor's to get to know her. | Clerk to invite Tina to a meeting.
28th April 2020 | Full Council | To ammend the online meeting protocol. | Clerk to action then upload to website.
14th January 2020 | Finance | Patchway Sports & Social Club to provide bills for payment. | Waiting to hear back from PSSC regarding this.
24th September 2019 | Parks | To ask 'Men in Sheds' if they could refurbish the benches in Scott Park. | Waiting to hear back from them.
22nd October 2019 | Parks | To investigate the formica Patchway 'You are Here' map. | Still to investigate.
26th November 2019 | Parks | To remove the teen shelter at Gorse Covert. | Not removed yet.
25th February 2020 | Parks | To obtain quotations for a watering device for planters and hanging baskets. | Office Administrator obtaining quotes.
25th February 2020 | Parks | To obtain quotations for a container for the compound at the Sports and Social Club. | Office Administrator obtaining quotes.

## Full Council
Patchway Town Council Action Tracker |  |  | 138 Actions
|  | Completed | 123
Committee | Full Council | Incomplete | 8
May 2019 - May 2020 |  | Superseeded | 7
This list doesn’t included the introduction of new policies.
Date of Meeting | Action | Status | Notes
14th May 2019 | Get independent report on the ability slide at Scott Park to ascertain whether is fit for use.
Clerk to circulate presentation for the Gypsy Patch Lane consultation to all Cllrs
Invite police to a future town council meeting.
Investigate whether Patchway Town Council's offices could be used as a drop off point for the food bank.
RFO produce an end of year forecast and quarterley reviews for budget against the forecast.
| Finance committee to consider four-year budget proposals. |  | Finance committee now considering a 3-year budget proposal.
To purchase a laptop for the Deputy Clerk.
11th June 2019 | £20,000 to 'New Projects' budget
| £21,419.66 CIL monies to be earmarked for 'Infrastructure'. |  | Superseeded by earmarking for 'Professional Fees'.
Cllrs to complete quarterley internal controls checks.
All groundstaff should have hi-vis PPE.
Appoint Louisa Hill to carry out the annual play inspection.
Request annual accounts from Patchway Sports & Social Club.
RFO to provide a breakdwon of petrol and diesel.
18th June 2019 | Southern Brooks to provide a calendar of events and PTC display on noticeboards.
| To consider an appropriate fees policy. |  | See 'Outstanding Actions' sheet
Clerk to write to local MP regarding the unfairness of the use of management companies on new developments.
Clerk to write to Bovis to have confirmation they want PTC to provide and empty dual use bins.
Clerk and RFO to establish costs to provide the bin service for Charlton Hayes.
Clerk to contact SGC to establish if the S106 monies can be used for professional fees.
Clerk to clarify if S106 monies can be used to rebuild the Pavilion rather than refurbish.
Clerk to write a letter to Mant Leisure saying that they would be liable for any injury or claim on the new ability slide.
| Proposal of a monthly newsletter via Mailchimp. |  | See 'Outstanding Actions' sheet.
Transfer £2000 to Staff Uniform budget.
Install beacons on both council vans.
To renew IRIS payroll software.
Clerk to email notes from Gypsy Patch Lane stakeholders group.
Clerk to issue a letter to Cllr K Walker to thank him for his service.
Clerk to circulate all correspondence from this meeting.
25th June 2019 | Temporarily close the offices on a Wednesday.
23rd July | To ammend the Extraordinary Council minutes on 25th June 2019 to add in the quoted context.
Clerk to contact AJBC with queries raised.
Appoint Stokes Morgan as Planning Consultants for the Scott Park project.
Deputy Clerk to seek clarification and costs from supplier for slide alterations and circulate to all members.
Remove the 'Patchway Vision' document from the Town Council website.
To purchase and set up 'Sky-guard' mandown device.
| Install broadband at Scott Park. |  | See 'Outstanding Actions' sheet.
Invite Mark King to the September Planning & Transport meeting with all Cllrs being invited.
To refresh the boardroom.
17th September 2019 | Officers to investigate if Electrical Installation Condition Reports are needed.
Ask Patchway Sports and Social to provide bills for electric re-charge.
PSSC end of year accounts are required.
The council need to draft a surveillance policy.
Purchase the sensory boards for Scott Park.
To carry out the utility search at Scott Park.
Clerk to provide council with a report regarding 'Wednesday Closures'.
1st October 2019 | To approach Melrose Associates and ask them to provide a quote for projet management of the PCC Redvelopment.
To approach South Gloucestershire to ask for an approved contractors list for project management.
14th October 2019 | To obtain quotations for a large TV/Monitor screen and invest in a laser pointer.
| To obtain signage for our benches and install as soon as possible. |  | Signs purchased 05/05/2020
Clerk to write a letter to Coniston Community Association expressing the council's discontent with the lack of care of the building and a full safety report be carried out.
Clerk to obtain risk assessments from Coniston Community Association.
Formally appoint Nick Morley for the PCC and Scott Park redevelopments.
Clerk and Deputy Clerk to join SLCC
To set up and implement councillor email addressess.
Deputy Clerk to create a Facebook event for VE Day celebrations.
| Clerk and Deputy Clerk to arrange monthly meetings with Bromford and Cllr I Walker. |  | Cllr I Walker to communicate via email.
To implement the VAT registration.
Clerk to query parking in response to planning application for 24 Thirlmere Road.
Clerk to object to planning application for 27 Swallow Drive.
Clerk to object to planning application for 5 Redfield Road.
Councillors to receive links to Planning Applications via email.
To implement the redundnacy policy after guidance from South West Councils.
19th November 2019 | The Clerk to write letter to Coniston Community Association trustees requesting urgent action is taken and a fire risk assessment is carried out.
Cllr K Dando to send photo's to the Clerk and Clerk will then circulate.
To review the Finance Committee's terms of reference.
| PTC to take a more active role in the Remeberance Parade in 2020. Clerk to set up a meeting with key stakeholders. |  | See 'Outstanding Actions' sheet.
To allocate £21.419.66 towards Professional Fees.
Appoint DCK accounting to carry out monthly checks of the finances.
To migrate the Server to an online platform.
Appoint Auditing Solutions LTD for 2020 to perform the audit.
| To hold two tree planting events in December 2019. |  | Cancelled due to weather conditions.
Formally appoint Nick Morley to get the 3G project to tender stage.
| To engage SGC in a walkaround in Spring 2020 to locate any new or highlight old issues. |  | See 'Outstanding Actions' sheet.
22nd November 2019 | The Clerk to invite all staff to a meeting on 4th December to discuss the presentation from South West Councils.
To install a hearing loop and monitor screen for the board room.
27th November 2019 | To ammend the Personnel Committee's terms of reference to include delegation as agreed to the Proper Officers.
Earmark £15,000 towards HR support.
17th December 2019 | To invite Martin Burton to a future meeting to discuss the funding for Patchway Library.
To inform Almondsbury Charity that they will have to pay for room hire.
To instruct JM Hazell to carry out works needed from the Fire Risk Assessment.
Inform all grant applicants of the council's decision.
To put an article on the Town Council website and Facebook regarding their support for residents with the current parking situation around Waterside Drive.
Review the Financial Risk regsiter twice a year.
| To hold the community planting event in January 2020. |  | Cancelled due to weather conditions.
To delegate £3000 to the Proper Officers to ensure a quick and appropriate repair to the drainage is actioned.
To formally appoint Melrose Associates to help with the tendering process for the PCC redvelopment project.
To invite Patchway Sports & Social Club to the Finance meeting in January 2020.
Clerk to object to the planning application for a temporary car park and to suggest the re-opening of Highwood Road.
20th December 2019 | To offer an agreement to the value of no more than £45,000.
21st January 2020 | To agree and publish the budget of £730,655.
| To invest £50, 283.57 into two separate funds. |  | £25,283.57 invested into CCLA. £25k into Cambridge and Counties.
To appoint Nick Morley as architect for the Pavilion project.
To appoint Stokes Morgan planning as consultants for the Pavilion project.
To formally appoint J Turner as RFO.
27th January 2020 | The Clerk, Deputy Clerk and Melrose would meet to discuss the revisions to the tender document for the 3G project.
To extend closure of council offices on a Wednesday until May 2020.
Cllr E Martin to reply to the MP's letter.
Cllr I Walker to raise issues with Honnister House to Bromford.
18th February 2020 | To change Standing Orders to reflect more clearly about public question time.
PTC to encourage all users of The Casson Centre to use the Town Council car park.
To Earmark £1000 for the VE Day Celebrations.
To circulate all hire charges to all regular hirers.
To instruct SGC to carry out the installation of lights at Scott Park.
Agreed the preferred suppliers list with the monetary limits at £1500 for sole traders and partnerships and £3000 for limited companies.
To ammend Financial Regulations to incorporate the preferred suppliers list.
To ammend Financial Regulations to incorporate the delegation of power to spend to the Clerk.
To instruct JM Hazell to carry out the works at Callicroft House.
To reduce cost of paper and printing by using the monitor for all meetings.
Transfer £82,583.51 to Unity Bank.
The Chairman to write a letter to J Thomas to thank him for his service to the community.
| Clerk to invite Tina Brice to a future meeting for councillor's to get to know her. |  | See 'Outstanding Actions' Sheet
Deputy Clerk to send Cllr I Walker the rejection letter for the Wednesday Lunch Clubs' grant request.
10th March 2020 | Deputy Clerk and Cllr R Loveridge to attend site visits for the 3G project. |  | David Wolstenholme attended instead
| Deputy Clerk and Cllr R Loveridge to attend a site visit with GW Parker to assess the tree work in Scott Park. |  | Site visit carried out 12/05/2020
Clerk to circulate all information for the PCC redvelopment project to the whole project group.
Clerk to arrange a meeting with PCC project group and Melrose.
To implement a Community Award Scheme.
To set an agreeable limit for the agreement.
17th March 2020 | Create a new budget heading for 2019/2020 called 'COVID-19 Emergency'
To circulate all planning applications during the Coronavirus pandemic to Cllrs T Bathe-Taylor, K Dando and E Martin
26th March 2020 | To open an investment account with Cambridge & Counties Bank
Purchase and implement the 'GO TO Meeting' software.
31st March 2020 | Cllr S Scott or Cllr G Pykov to review the 3G tender documents.
14th April 2020 | Earmark CIL money for the Pavilion project professional fees.
Clerk to organise tender opening process for the 3G project.
To arrange a meeting with Cllr S Scott and South West Councils.
21st April 2020 | Issue certificates to all community award winners
Ammend the minutes of 18th February 2020 to correct the spelling of Cllr Shambhu's name.
Ammend the minutes of 7th April 2020 to include a statement about the haste of the insurance quotes.
Ammend the minutes of 14th April 2020 due to Cllr R Loveridge having technical difficulties with the meeting software.
To obtain quotations for a different architect for the pavilion project.
Send the S106 agreement for Blakeney Road Basketball project to South Glos.
| The project manager for the 3G project will complete a tender evaluation report. |  | Expected to be issued w/c 11th May 2020
To obtain legal advice pertaining to a lease agreement.
28th April 2020 | To ammend the online meeting protocol. |  | See outstanding actions sheet'
To inform the professional services for the pavilion project that they had been succesful/unsuccesful
To serve the notice from the solicitor.

## Finance
Patchway Town Council Action Tracker |  |  | 24 Actions
|  | Completed | 21
Committee | Finance | Incomplete | 1
May 2019 - May 2020 |  | Superseeded | 2
Date of Meeting | Action | Status | Notes
9th July 2019 | To ammend the terms of reference to read 'All members of Full Council, not in the Finance Committee, may attend and participate in the meeting but non finance committee members have no voting rights.
All future summons to clearly identify which councillors are members of which committee.
| To review the option for 5 year planning. |  | PTC will now look at 3-year budget plans.
A letter of complaint to be sent to NatWest regarding poor service.
10th September 2019 | Recommend that the Council pruchases cyber insurance.
8th October 2019 | Cllr S Scott to meet with Deputy Clerk to discuss revenue and capital breakdown.
To let other committees comment on the Financial Risk Register.
Deputy Clerk to review all budget codes.
To obtain clear copies of the Bank Statements.
12th November 2019 | Ammend the October minutes the ammendment to show 'decide' rather than 'decided' on item 8.
To send the draft budget to all committees for review.
To clear the cheque off the system for Denmans which was 11 months old.
10th December 2019 | To revise the budget as per the minute reference 10/12/2019 NO.5.
To look at different investment options and report back in January 2020.
14th January 2020 | To instruct the Parks committee to look at possible locations for CCTV.
| Patchway Sports & Social Club to provide bills for payment. |  | See 'Outstanding Actions' sheet.
To remove the £34,500 for a possible PWLB loan from the budget.
To ammend the Terms of Reference to read 'Nine' members.
To pursue the reccomendation for the value of £509.
11th February 2020 | Agree to recommend the 3 year budget as a working document.
Move the monies for tree work into the 'Pretoria Road' budget heading.
| To consider premium bonds as an investment. |  | Premium Bonds cannot be accesed by the Town Council.
Ammend the 'Financial Procedure' document to include the word 'signed' on page 5.
10th March 2020 | Recommend to Council to invest £25,000 into Cambridge & Counties Bank.

## Parks & Open Spaces
Patchway Town Council Action Tracker |  |  | 39 Actions
|  | Completed | 31
Committee | Parks and Open Spaces | Incomplete | 5
May 2019 - May 2020 |  | Superseeded | 3
Date of Meeting | Action | Status | Notes
25th June 2019 | Parks Working Group to look at the Play Area Strategy with Deputy Clerk.
Clerk to delay the annual play inspection until the slide is installed at Scott Park.
| To review the Allotment Association handbook and discussed with Pretoria Road Allotment representative. |  | Pretoria Road Allotment Society to look at this
Clerk to arrange a meeting with Pretoria Road Allotments to discuss a number of issues.
Chairman to contact resident regarding the Park Run.
Clerk to check with legal advisers/insurers about the language on the new signs.
To install new signs on all play areas.
Clerk to establish what PTC's responsibilities are for the changing rooms at Patchway Sports & Social Club.
To obtain quotes for a pedestrian mower.
30th July 2019 | To send a partial payment for the Ability Slide.
To circulate the revised football terms and conditions.
Working Group to consider Fire Risk Assessment costs.
Replace the seesaw seat at Bevington Play Area.
Service all goal posts and replace the clips.
To instruct the contractor to tidy up the 'copse' area at Scott Park.
To ammend the weekly play area safety sheets to include 'ok; minor damage/needs repair; not fit for use.
Clerk to approach Highways England and YTL to see if they can offer assistance with the bund at Bevington Walk.
24th September 2019 | To instruct the contractor to undertake the percoloation tests.
| To obtain quotations for tree work around Patchway. |  | Preferred suppliers list created.
Organise a Parks working group walkaround with SGC representatives.
To put in a bid for the S106 monies to enahnce Basketball facilities.
To ask 'Men in Sheds' if they could refurbish the benches in Scott Park.
22nd October 2019 | To invite residents to the community planting event at the Tumps, Gorse Covert and Centre of Highwood Road.
To make ammendments to the Financial Risk Register as per minute reference 22/10/19- No 8.
To purchase 'No Dog' signs for Scott Park
To investigate the formica Patchway 'You are Here' map.
26th November 2019 | To set budget codes as per minute reference 26/11/19 - No 6.
To adopt the 'Play Area' strategy and review monthly.
To communicate the Christmas Tree recycling locations on PTC website and Facebook.
To remove the teen shelter at Gorse Covert.
28th January 2020 | To organise a working group to meet with Patchway Sports and Social Club regarding CCTV.
To obtain quotations for the S106 Basketball agreement.
To add 'GW Parker' to prefered suppliers list for 'Tree Work'.
| To instruct Groundstaff to plant the saplings around the town. |  | Bedded in, in Scott Park.
25th February 2020 | To populate the S106 agreement for the Basketball facility.
To communciate the extension of 7th May for Youth Football at Scott Park.
To obtain quotations for a watering device for planters and hanging baskets.
Apply for the Sport England Community Asset Fund grant.
To obtain quotations for a container for the compound at the Sports and Social Club.

## Planning & Transport
Patchway Town Council Action Tracker |  |  | 13 Actions
|  | Completed | 13
Committee | Planning and Transport | Incomplete | 0
May 2019 - May 2020 |  | Superseeded | 0
Date of Meeting | Action | Status | Notes
25th June 2019 | Clerk to chase ALCA for planning training for Cllrs.
Clerk to invite Mark King to a future meeting.
Clerk to find out if repeater traffic speed signs should be in place on Rodway Road.
24th September 2019 | To write to SGC and district councillors to call in application for 5 Redfield Road.
Deputy Clerk to write to Bromford and SGC for railings to be treated at the Parade.
22nd October 2019 | To instruct SGC to erect the xmas lights.
To clarify with ALCA if xmas lights can be sponsored whilst the council doesn’t have GPC.
To ammend the draft risk register as per minute reference 22/10/19 - No 7.
| Happy to Chat Bench' stencil to be investigated. |  | Signs purchased May 2020.
26th November 2019 | To ammend the draft budget as per munute reference 26/11/19 - No 5
28th January 2020 | To object to all tree applications given the climate emergency.
To object to the application for 5 Redfield Road.
25th February 2020 | To object to the application for a 'Temporary Car Park'.