## Outstanding Actions
|  | PTC May 2020 -April 2021 Outstanding Actions | Year To Date Completed | 279
|  |  | Year to Date Incomplete | 3
|  |  | Year to Date Superseeded | 2
|  |  | Total Actions | 284
|  |  | Carried Forward from 19/20 | 13
|  |  | 19/20 Completed or Superseeded | 13
|  |  | 19/20 Outstanding | 0
Actions will be added here if they are not completed in the three weeks after the meeting has taken place.
Date | Committee | Action | Notes | Status
|  | 19-20 OUTSTANDING | 19-20 OUTSTANDING
18th June 2019 | Full Council | To consider an appropriate fees policy. | Policy drafted for approval at earliest opportunity.
18th June 2019 | Full Council | Proposal of a monthly newsletter via Mailchimp. | Can be done for free via The Town Council's website and social media. Proposal going to Council in 2020.
23rd July 2019 | Full Council | Install broadband at Scott Park. | Charges were to high to be considered. Investigation ongoing.
19th November 2019 | Full Council | PTC to take a more active role in the Remeberance Parade in 2020. Clerk to set up a meeting with key stakeholders. | Clerk still to arrange a meeting with Key Stakeholdets.
19th November 2019 | Full Council | To engage SGC in a walkaround in Spring 2020 to locate any new or highlight old issues. | Deputy Clerk to arrange for after COVID-19 outbreak.
18th February 2020 | Full Council | Clerk to invite Tina Brice to a future meeting for councillor's to get to know her. | Clerk to invite Tina to a meeting.
28th April 2020 | Full Council | To ammend the online meeting protocol. | Clerk to action then upload to website.
14th January 2020 | Finance | Patchway Sports & Social Club to provide bills for payment. | Waiting to hear back from PSSC regarding this.
24th September 2019 | Parks | To ask 'Men in Sheds' if they could refurbish the benches in Scott Park. | Waiting to hear back from them.
22nd October 2019 | Parks | To investigate the formica Patchway 'You are Here' map. | Still to investigate.
26th November 2019 | Parks | To remove the teen shelter at Gorse Covert. | Quotation received for Council meeting in May/June 2021.
25th February 2020 | Parks | To obtain quotations for a watering device for planters and hanging baskets. | Office Administrator obtaining quotes.
25th February 2020 | Parks | To obtain quotations for a container for the compound at the Sports and Social Club. | Office Administrator obtaining quotes.
|  | MAY 2020 - APRIL 2021 | MAY 2020 - APRIL 2022
20th October 2020 | Full Council | To draft a business plan for the rental or sale of Callicroft House. | Local Groups have been in contact about rental of the building.
26th April 2021 | Full Council | To write to the Exectutive Member at SGC regarding Highwood Road.
26th April 2021 | Full Council | To arrange a meeting with Beard to reach the middle ground.

## Full Council
Patchway Town Council Action Tracker
|  | Completed | 169
Committee | Full Council | Incomplete | 3
May 2020 - April 2021 |  | Superseeded | 2
This list doesn’t included the introduction of new policies.
Date of Meeting | Action | Status | Notes
19th May 2020 | Inform outside organisations of the councillors who be the PTC representative.
19th May 2020 | Circulate the 3-year budget plan to all councillors.
19th May 2020 | Publish policies onto website.
19th May 2020 | To organise a grants working party to look at grants.
19th May 2020 | To publish the new risk register on the website.
19th May 2020 | To inform Nick Morley of appointment as The Principal Designer for the PCC project.
19th May 2020 | To inform the succesful tender applicants and arrange a meeting with bidder 1.
19th May 2020 | To pay all authorised invoices.
19th May 2020 | To issue certificates to all award winners.
19th May 2020 | To take any comments and publish the 2020 Annual Report.
19th May 2020 | To obtain a quote from SGC for outside areas grass cutting.
19th May 2020 | To circulate all planning applications to working party.
1st June 2020 | Asking SGC Streetcare to help maintain area's for three months.
1st June 2020 | To refer the funding agreement to the solicitor to comment on for the PCC Redvelopment Project.
16th June 2020 | Publish Finance Committee terms of reference on the website.
16th June 2020 | Ammend Financial Regulation 4.1
16th June 2020 | Clerk to send out tender for PCC redvelopment
16th June 2020 | Ammend the preffered suppliers list.
16th June 2020 | Obtain quotes for security at Scott Park.
16th June 2020 | To inform applicants of the outcomes from the grant's report.
16th June 2020 | To earmark £2250 for ReACH.
18th June 2020 | Publish re-adopted policies on website.
18th June 2020 | To issue certificates to all award winners.
18th June 2020 | The Clerk to organise a site visit with reference to the proposed Newnham Place development.
18th June 2020 | To circulate planning applications to three Councillors as delegated.
18th June 2020 | To feedback the Council's thoughts on the new waiting restrictions.
18th June 2020 | Clerk to write letter along with SGC Councillors with reference to the funding of Patchway Library.
30th June 2020 | To send the signed funding agreement back to SGC.
30th June 2020 | To inform NSG about the acceptance of their quote and arrange the security for Scott Park.
30th June 2020 | To inform Ecosolve about the acceptance of their quote and arrange for the work to be carried out.
30th June 2020 | To inform Virgin Media about the acceptance of their quote and query the installation costs.
21st July 2020 | To publish terms of reference for the Parks, Open Spaces, Planning and Transport committee on the website.
21st July 2020 | To amend financial regulation 4.1.
21st July 2020 | To earmark £1205.18.
21sr July 2020 | To inform GB Sports and Leisure about the acceptance of their quote and organise for the products to be delivered.
21st July 2020 | To send around the terms and conditions for football pitch hire.
21st July 2020 | To inform Patchway Town FC about the 3G pitch hire arrangement.
21st July 2020 | To inform Patchway Cricket Club about the cricket nets arrangement.
21st July 2020 | To arrange a meeting to dicuss the 3 year budget plan.
21st July 2020 | To move £82457 into the CCLA deposit fund.
21st July 2020 | To inform applicants of the outcomes from the grant's report.
21st July 2020 | To set up a COVID-19 response budget.
21st July 2020 | To publish the internal audit report with the answered reccomendations on the website.
21st July 2020 | To authorise payments.
21st July 2020 | Chairman to write letter Ted Bathe-Taylor to thank him for his service.
21st July 2020 | To task the solicitor with getting an answer regarding the lease agreement.
27th July 2020 | Inform Patchway Sports and Social club of the decision to allow the event to take place.
27th July 2020 | To inform Patchway Sports and Social about the deferal of ground rent payments until November 2020.
27th July 2020 | To inform ReACH that Cllr J Buddaraju was single point of contact.
27th July 2020 | Council to request Chamonix and Bovis draft budget for next five years.
27th July 2020 | To investigate whether land at Charlton Hayes can fall under PTC's remit.
27th July 2020 | To investigate staff's time on Charlton Hayes matters.
27th July 2020 | To publish the re-adopted policies.
27th July 2020 | To issue certificates to all award winners.
27th July 2020 | To inform Martin Burton that the Council will fund the agreed amount for 2020/21.
27th July 2020 | To inform NSG that the Scott Park security is to continue.
27th July 2020 | The Clerk will obtain legal advice on the Newnham Place development and pass it onto Cllr S Shambu to raise with SGC.
27th July 2020 | To publish the adopted policies.
27th July 2020 | To send the revised funding agreement to SGC and to thank the residents of Patchway and Charlton Hayes for funding this development.
27th July 2020 | To inform the Bush Conusultancy of their appointment to the Patchway CC project.
11th August 2020 | Inform Beard that the Council have chosen them as the preferred contractor subject to qualifications.
11th August 2020 | The Clerk to inform Beard of the award of contract was qualifications are covered.
11th August 2020 | To look into other security company costs for Scott Park.
11th August 2020 | To inform Alf Sollars that the Council agreed to the Rememberance Event.
11th August 2020 | To sign and publish all end of year documentation.
20th August 2020 | To set up a new lease between PTC and Bristol BMX club for 20 years.
20th August 2020 | To set up a working party meeting to discuss the way forward.
26th August 2020 | To inform contractors that Jon Butler would be the honorary appointed advisor for the 3G and Cricket Nets project.
15th September 2020 | To publish all agreed minutes on the website.
15th September 2020 | To move £5000 from EMR to a New Projects budget.
15th September 2020 | To introduce a youth pricing bracket for the 3G pitch.
15th September 2020 | To notify the accountant that he will only be needed for quarterly checks.
15th September 2020 | To inform Prostructures of their appointment.
15th September 2020 | To arrange a working group of the Patchway Community Centre redevelopment project.
15th September 2020 | To inform Watt Design of their appointment.
15th September 2020 | To inform Southern Brooks who the working group of Councillors will be.
15th September 2020 | The Chairman to write back to the Mayor of Clermont to provide an update on the thing's happening in Patchway.
15th September 2020 | The Deputy Clerk to ensure Cllr Buddharaju is invited to all ReACH meetings.
15th September 2020 | Clerk to raise objection to the 4 Stroud Road planning application.
15th September 2020 | Clerk and Vice-Chairman to agree insurance for the Patchway Community Centre Redvelopment Project.
15th September 2020 | The staff to work back in the offices.
15th September 2020 | To inform staff of the Council's stance on quarantine.
15th September 2020 | To purchase a satellite office if below £5000.
15th September 2020 | To send a letter to the lessee detailing the advice and try to arrange a meeting.
20th October 2020 | To publish the terms and conditions for 3G pitch and the cricket nets.
20th October 2020 | To order 3 benches to cemmorate VE Day.
20th October 2020 | To dissolve the Scott Park advisory committee and inform all members of the merger with the Parks, Open Spaces, Planning and Transport committee.
20th October 2020 | To move £20,000 to EMR 'New Projects'.
20th October 2020 | To ammend the preferred suppliers list.
20th October 2020 | To publish the three year strategic plan for public consultation.
20th October 2020 | To inform all grant applicants of the outcome of their application.
20th October 2020 | To remove the EMR for ReACH Grant.
20th October 2020 | To write to SGC regarding the Highwood Road Consultation.
20th October 2020 | To draft a business plan for the rental or sale of Callicroft House.
20th October 2020 | To inform Melrose about drafting the NEC 4 contracts.
20th October 2020 | To inform all award winners of their award.
20th October 2020 | To instruct Blakedown to fix the kickboards on the 3G pitch.
20th October 2020 | To implement the NJC Pay Award.
20th October 2020 | Implement all reccomendations from Personnel Committee.
17th November 2020 | To send a response to South Gloucestershire Council reference Highwood Road.
17th November 2020 | To order a COVID-19 memorial bench
17th November 2020 | To purchase a Magnolia Tree as part of the COVID-19 memorial.
17th November 2020 | To invest more money into the CCLA and the RFO be responsible for the amounts transferred.
17th November 2020 | Send £500 donation to the Patchway Branch of Royal British Legion.
17th November 2020 | Action the reccomendations from the Internal Auditor's report.
17th November 2020 | To ask the contractor to carry out the lighting survey of the 3G pitch.
17th November 2020 | To create a protocol for community awards and set up a meeting between the Clerk, RFO Chairman and Vice-Chairman to discuss.
17th November 2020 | Cllr S Scott to write to the police to thank them for their tireless efforts during COVID-19.
17th November 2020 | To signpost available grants and support to Patchway Sports and Social Club.
15th December 2020 | To add a contractor onto the preferred suppliers list.
15th December 2020 | To ask the project manager to start the tender on the NSP Pavilion project.
15th December 2020 | To send the precept request to South Gloucestershire Council for 2021/2022.
15th December 2020 | To publish the adopted three year plan.
15th December 2020 | To name the 3G facility the 'Jason Franklin 3G Facility'.
15th December 2020 | To hold a separate meeting to discuss filling out the form for Highwood Road traffic order review.
15th December 2020 | To email the sports and social club to make them aware of their rent defferals.
19th January 2021 | To clarify some points on the Patchway waiting restrictions review.
19th January 2021 | To publish the new hire rates.
19th January 2021 | To raise cover of fidelity insurance for a temporary period.
19th January 2021 | To inform the project manager and architect that their fee proposals had been accepted.
19th January 2021 | To inform Mama's Bristol CIC of their grant award.
19th January 2021 | To publish the new risk register.
19th January 2021 | To split the Parks, Open Spaces, Planning and Transport agenda into sections to separate matters pertaining Parks and Planning.
19th January 2021 | To arrange a book of rememberance.
19th January 2021 | To get the photo competition up and running.
19th January 2021 | Clerk to raise an objection to the application.
19th January 2021 | To invite the sports and social club to a Finance committee meeting.
16th February 2021 | To inform the contractor to undertake the installation of a basketball court.
16th February 2021 | Transfer £5000 from EMR to the Blakeney Road basektball project.
16th February 2021 | To publish the new room hire rates.
16th February 2021 | To inform the sports and social club that their rent has been defferred until April 2021.
16th February 2021 | The RFO to write back to Mark King ref fly tipping.
16th February 2021 | The Personnel Committee to see if it would be viable to use PTC staff to clear back lanes.
16th February 2021 | To apply for the £5000 'Love Our High Street' grant.
16th February 2021 | To submit 'Local Plan' responses to SGC.
16th February 2021 | RFO to look into Patchway People Grant from TNL.
16th February 2021 | To arrange a book of rememberance quotation.
16th February 2021 | To implement holiday pay deduction for staff not in work due to COVID-19.
16th February 2021 | To look at alternative staffing solutions.
17th February 2021 | To inform all professional services they have been approved for NSP Pavilion project.
17th February 2021 | To populate the form for Highwood Road consultation.
17th February 2021 | To set up online survey for Highwood Road consultation.
8th March 2021 | Clerk to contact SGC planning officers regarding the Council's stance on the Blakeney Road development.
16th March 2021 | To discuss financially supporting Mama's Bristol CIC. at the next Council meeting.
16th March 2021 | To purchase a bin to be installed at the opening of 'ASDA Lane'.
16th March 2021 | To earmark £200,000 towards the NSP Pavilion project.
16th March 2021 | To vire £25,000 to the NSP Pavilion project.
16th March 2021 | To vite £10,000 to the new projects budget.
16th March 2021 | To inform all contractors they have been chosen for the NSP Pavilion project.
16th March 2021 | To send the approved Highwood Road form and appendices to South Gloucestershire Council.
16th March 2021 | To purchase the book of rememberance.
16th March 2021 | To upload the grant awarding policy and form to the website.
16th March 2021 | To invite Patchway People committee to the April meeting of the Finance Committee.
16th March 2021 | To hold meetings with affected staff (Closed session).
16th March 2021 | To hold a lease agreement working party.
26th April 2021 | To complete the PWLB Loan Application and send to Avon Local Council's Association.
26th April 2021 | To arrange a meeting with the Youth Work sub-committee.
26th April 2021 | To communicate to all teams that the hire fees would not be reduced for football pitch hire.
26th April 2021 | To notify Patchway Festival of their grant award.
26th April 2021 | To obtain quotations for sports coaching sessions.
26th April 2021 | To hold a PQQ opening sessions for NSP Pavilion project.
26th April 2021 | To inform Shield of their approved quotation.
26th April 2021 | To inform David Wolstenholme that the Council have agreed the plans for NSP Pavilion.
26th April 2021 | To inform the cricket club of the hire charge rate.
26th April 2021 | To publicise free hire of the cricket nets until July for Under 14's.
26th April 2021 | To set up a working group to meet with Mama's Bristol CIC.
26th April 2021 | To contact Circus Ginnett to obtain further information.
26th April 2021 | To obtain quotes for the removal of bus shelters.
26th April 2021 | To write to the Exectutive Member at SGC regarding Highwood Road.
26th April 2021 | To implement the Charlton Hayes Litter Picker scheme.
26th April 2021 | The Clerk to look into employing a street cleaner for Charlton Hayes.
26th April 2021 | The Deputy Clerk and Cllr B Hopkinson to write to SGC about the Britannia Road Planning Application.
26th April 2021 | To arrange a meeting with Beard to reach the middle ground.
26th April 2021 | To obtain costs for a street cleaning machine.
26th April 2021 | To inform PSSC of the rent deferral.
26th April 2021 | To appoint a barrister.

## Finance
Patchway Town Council Action Tracker
|  | Completed | 20
Committee | Finance | Incomplete | 0
May 2020 - April 2021 |  | Superseeded | 0
Date of Meeting | Action | Status | Notes
12th May 2020 | Produce an expected expenditure VS budget document for the next meeting.
12th May 2020 | Circulate three-year budget to all committees.
9th June 2020 | Ammend the terms of reference.
9th June 2020 | Amend Financial Regulations.
9th June 2020 | To obtain quotations for an external company to maintain the planters.
9th June 2020 | Add in column for 2019/2020 budget in three year plan.
14th July 2020 | Ammend the three year plan to correlate with resolutions.
8th September 2020 | To investigate paying off the PWLB loan in full before the end date.
10th November 2020 | To ammend the budget document as per resolutions.
10th November 2020 | To purchase mobile broadband hub for Scott Park.
8th December 2020 | To ammend the budget to show a large capital amount to match the precept from 2020/2021.
12th January 2021 | The RFO to gather a report on costs of room hire in the local area.
9th February 2021 | To ask SBCP to apply for an emergeny grant.
9th February 2021 | RFO and Cllr Buddharaju to ask SBCP and SGC for more information into the funding of youth work in Patchway.
9th February 2021 | To inform the contractor that their quote had been accepted.
9th March 2021 | To inform Ecosolve that their quotation had been approved.
9th March 2021 | To lead on discussing the way forward for youth work in Patchway.
9th March 2021 | To contact Cllr E Martin to carry out an internal controls check.
20th April 2021 | To inform the Councillor that they can make a donation for surplus equipment.
20th April 2021 | RFO to circulate links to other online publications.

## Parks & Planning
Patchway Town Council Action Tracker
|  | Completed | 90
Committee | Parks & Planning | Incomplete | 0
May 2020 - April 2021 |  | Superseeded | 0
Date of Meeting | Action | Status | Notes
23rd June 2020 | To ammend the terms of reference.
23rd June 2020 | To ammend Financial Regulations.
23rd June 2020 | To inform co-opted members that they have been succesful.
23rd June 2020 | Investigate grant monies for FA funded sports equipment.
23rd June 2020 | To ammend the three year budget plan as per resolutions.
23rd June 2020 | To ammend the terms and conditions for the Football Pitch Hire.
23rd June 2020 | To instruct Ecosolve to carry out the rennovation work at Scott Park.
23rd June 2020 | To inform Just Plants Bristol to carry out the work on the planters.
23rd June 2020 | To purchase the bin for Waterside Drive and to install it.
23rd June 2020 | Deputy Clerk to write to Bovis about the Linear Park.
23rd June 2020 | To put out an online survey asking residents where they would like the 'Happy to Chat' signs placed.
28th July 2020 | To erect the 'Happy to Chat' signs on the locations approved.
28th July 2020 | The Clerk to chase up the Rodway Road signage.
28th July 2020 | To set up a working group.
28th July 2020 | To research options for a bench for a COVID memorial and tree to be erected in Scott Park.
22nd September 2020 | To get some images of the proposed new gates.
22nd September 2020 | To ammend the terms and conditions for the 3G pitch.
22nd September 2020 | To ammend the terms and conditions for the 3G pitch.
22nd September 2020 | To obtain quotations for a basketball court at Blakeney Road Play Area.
22nd September 2020 | To set up a working group to arrange the Rodway Road planting event.
22nd September 2020 | To inform the BMX club that they can pollard the trees.
22nd September 2020 | Deputy Clerk to check with Bovis about suitable locations.
22nd September 2020 | To obtain a quotation for the lights identified.
22nd September 2020 | To refer the A38 project onto Stoke Lodge and The Common Parish Council.
22nd September 2020 | To remove the sensory garden in Scott Park.
22nd September 2020 | To invite Mark King to the October meeting and invite residents to come and give their views.
27th October 2020 | Obain quotes for new gates.
27th October 2020 | Instruct Louisa Hill to undertake the annual play inspection.
27th October 2020 | Instruct CR Fencing to carry out the repair work.
27th October 2020 | Obtain quotes for wooden and steel benches for The Tumps.
27th October 2020 | The Clerk to write to South Gloucestershire Council about the boundary at Pretoria Road Allotments.
27th October 2020 | To organise a meeting with delegated members about Christmas Lights.
27th October 2020 | To raise an objection to a planning application
27th October 2020 | Deputy Clerk to liaise with the Conservation Group about the tree bundles.
24th November 2020 | Deputy Clerk and select members to hold a meeting about setting up a sports academy.
24th November 2020 | Obtain quotes for a tarmac/wet-pour surface for the basketball facility.
24th November 2020 | To order the six wooden benches for the Tumps.
24th November 2020 | To order the new trailer.
24th November 2020 | To start the design process of the Patchway map.
24th November 2020 | Inform contractor to carry out the tree work.
24th November 2020 | Clerk to raise an objection on planning application and inform the district councillors of the objection.
24th November 2020 | To move the noticeboard at Arlingham Way Pocket Park into the play area.
24th November 2020 | To budget for a VE Day Bench for Charlton Hayes.
22nd December 2020 | To inform Gatesplus of the acceptance of their quote.
22nd December 2020 | To obtain more information for the Blakeney Road basketball facility.
22nd December 2020 | To obtain costings for a map idea and start to draft the idea of a map.
22nd December 2020 | Set up a sub-committee to look at noticeboards.
22nd December 2020 | Include the Patchway Waiting Restrictions in the next Council meeting.
22nd December 2020 | To arrange a sub-committee to look at locations in Scott Park for a COVID-19 memorial.
26th January 2021 | To order the steel structure.
26th January 2021 | To send ammendments of the map back to the print company.
26th January 2021 | Obtain quotes for seating at 3G facility.
26th January 2021 | Obtain quotes for singular goal post in Scott Park and Gorse Covert.
23rd February 2021 | To order the new goal posts for Scott Park pitches.
23rd February 2021 | To inform the contractor to carry out the tree work.
23rd February 2021 | To order the benches for around the 3G and obtain quotes for a tarmac surface.
23rd February 2021 | To investigate whether to remove the container or if it can be flat packed.
23rd February 2021 | To order the four new spring rockers.
23rd February 2021 | To make the ammendments to the Patchway Map.
23rd February 2021 | To obtain quotes for one goal post at Scott Park.
23rd February 2021 | RFO to gather more information on the path at Blakeney Road.
23rd February 2021 | To arrange a meeting with SGC to discuss management plan for Gorse Covert.
23rd February 2021 | To arrange a meeting of the working group.
23rd February 2021 | To arrange a working group meeting to discuss Newnham Place.
23rd February 2021 | To set up a Council meeting to discuss community housing developments.
23rd February 2021 | To invite Mark King to discuss speeding around Patchway.
23rd March 2021 | To inform KT Properties LTD that their quote had been accepted.
23rd March 2021 | To inform N Brock that his quote had been accepted.
23rd March 2021 | To inform GB Sports that their quote had been accepted.
23rd March 2021 | To inform Iron Man metal recycling their quote had been accepted.
23rd March 2021 | To re-draft the map artwork then comission.
23rd March 2021 | To arrange a working group.
23rd March 2021 | To set up two memorial planters in Scott Park.
23rd March 2021 | Deputy Clerk to circulate a site plan for benches at Scott Park.
23rd March 2021 | To hold the next meeting at 7:30pm due to the Annual Meeting of the Parishioners.
27th April 2021 | To inform dragon play and sports of the acceptance of their quote for the new slide.
27th April 2021 | Seek a quotation for a repair to the Pretoria Road gates.
27th April 2021 | To inform Ecosolve that the quote for end of season rennovations had been accepted.
27th April 2021 | To draft an agreement for Cricket Pitch Maintenance.
27th April 2021 | To ammend the signs and inform Rob Hainey of quote approval.
27th April 2021 | To organise a working group meeting.
27th April 2021 | To arrange a site visit with the head of Coniston Primary School.
27th April 2021 | To obtain quotations for large signs for Scott Park.
27th April 2021 | To obtain quotations for football equipment storage.
27th April 2021 | To look into how PTC can fund new sub benches.
27th April 2021 | Deputy Clerk to draft a report for the old sensory garden for the next meeting.
27th April 2021 | Look into more information about the fence line at allotments.
27th April 2021 | To obtain quotations and permission for installing dog bag dispensers in Charlton Hayes.
27th April 2021 | To obtain a quotation to move the noticeboard from Park Leaze inside Blakeney Road Play Area.